# PLMS Platform Upgrade - Impact, Effort and Risk

Prepared: 16 September 2026   |   Property & Lease Management System (PLMS)

# 1. Executive summary

PLMS runs on Laravel 5.7 (released September 2018, out of support since 2019) and PHP 7.3 (out of support since December 2021). Both are several major versions behind. This document explains what an upgrade involves, what will change or break, the effort and risk, and a recommended path.

Key points

- The upgrade cannot be done half-way: Laravel 5.7 does not run on PHP 8, and modern PHP 8 libraries do not run on Laravel 5.7. The realistic target is PHP 8.2 with Laravel 10, which is five major framework versions in one step.

- The code base is in better shape than expected for its age: no obsolete PHP language constructs were found, and the database layer (PostgreSQL functions and views) is unaffected.

- The main work is in third-party packages (four must be replaced, one of them is the Dynamics AX integration), about 170 helper-function calls to update, PDF/report re-verification, and – above all – manual regression testing across roughly 800 screens and 150 reports, because the system has almost no automated tests.

- Estimated effort: 7 to 10 weeks with one developer plus business users for testing, on a dedicated test server.

- One urgent finding independent of the upgrade: all 152 JasperReports templates (about 120 live reports) are stored inside the vendor folder, which is not in version control and is deleted by a routine dependency install. They should be moved into the project immediately.

- Recommendation: move the report templates now, move production PHP to 7.4 now (low risk, already verified), and schedule the full upgrade as its own project after the mobile app Phase 1 is delivered, so the two do not multiply each other's testing effort.

# 2. Current state

| Item | Current | Status |
| --- | --- | --- |
| PHP (production server) | 7.3 | End of life December 2021 – no security fixes |
| Laravel framework | 5.7.28 | End of life 2019 – no security fixes |
| Database | PostgreSQL | Fully supported; not affected by the upgrade |
| Reporting | JasperReports (Java) for ~120 reports; dompdf/FPDF/Excel for ~25 newer reports | Works; templates stored in an unsafe location (see section 6) |
| ERP link | Dynamics AX via SOAP (third-party package) | Package abandoned by its author |
| Code size | 1,325 PHP files, 809 screen templates, 6 modules | – |
| Automated tests | 9 unit tests (all added in 2026) | Almost everything must be tested by hand |

# 3. Options

| Option | What it is | Effort | Risk | Outcome |
| --- | --- | --- | --- | --- |
| A. Do nothing | Stay on PHP 7.3 / Laravel 5.7 | None | Growing: no security patches; every new library must be an old version; skills harder to find | Status quo |
| B. Minimal step | Move production to PHP 7.4, keep Laravel 5.7 | Half a day + smoke test | Very low – all recent development is already verified on PHP 7.4 | Slightly newer runtime; no new capabilities |
| C. Full upgrade (recommended, scheduled) | PHP 8.2 + Laravel 10 | 7–10 weeks | Medium – controllable with a test server and structured regression | Supported platform, modern libraries, easier hiring and maintenance |
| D. Rewrite | New application | Many months | High | Out of scope of this document |

# 4. What will change in the full upgrade (Option C)

## 4.1 Packages that must be replaced

| Package | Used for | Change | Impact |
| --- | --- | --- | --- |
| Laravel SOAP wrapper (artisaninweb) | Dynamics AX posting of receipts, invoices, vendors, tenants | Abandoned; replace with a small in-house wrapper around PHP's built-in SOAP client | Highest risk. Needs an AX test environment and end-to-end verification of every posting type |
| Breadcrumbs (davejamesmiller) | Page breadcrumbs | Abandoned; replaced by a maintained fork with the same API | Low – configuration and 6 route files |
| Proxy handling (fideloper) | Trusted proxies | Removed; built into Laravel | Low – one middleware |
| JasperPHP (cossou) | Runs JasperReports through Java | Unmaintained but framework-independent; keep | Low – but see section 6 |

## 4.2 Packages that jump several major versions

| Package | Used for | Impact |
| --- | --- | --- |
| Roles and permissions (spatie) v2 → v6 | Every menu and permission check | New database migrations and configuration; existing role checks keep working. Medium |
| Modules (nwidart) v4 → v11 | The 6 application modules | Module configuration and route registration change in all 6 modules. Medium |
| PDF engine (dompdf) v0.8 → v3 | Receipts, invoices, inspection reports, service reports | Rendering engine changed; every PDF must be visually re-checked. Medium |
| QR code v2 → v4 | QR on rent receipts | Server needs the ImageMagick PHP extension. Low |
| HTTP client (Guzzle) v6 → v7 | SMS gateway, AX | Minor code changes. Low |
| Date library (Carbon) v1 → v2 | Every date on every screen | Dates in JSON/AJAX responses change format; 50 database models need their date declarations updated. Medium |
| Test framework (PHPUnit) v7 → v10 | Unit tests | Low |
| Excel export, mPDF, image handling, activity log | Reports, thumbnails, audit | Minor version bumps only. Low |

## 4.3 Application code changes

| Area | Finding | Work |
| --- | --- | --- |
| Removed helper functions | 174 calls to helper functions that Laravel 6 removed (e.g. array_flatten, str_slug) | Mechanical replacement; low risk |
| Routes | All module routes use the old "Controller@method" text style | Keep the namespace setting in each module; otherwise every page 404s. Low once known |
| Paging | Laravel 8 changed the default paging style | One configuration line; low |
| E-mail | Laravel 9 replaced the mail engine | All 47 e-mails use the standard Mailable pattern – expected to work unchanged. Low |
| Dates | Newer Laravel serialises dates differently | Any AJAX grid or JSON that shows dates must be checked. Medium |
| PHP 8 strictness | PHP 8 raises errors where PHP 7 silently continued: arithmetic on empty text (e.g. an empty amount field), functions receiving null | Amount-handling code in receipts, terminations, inspections and reports needs explicit type conversion. Found only by testing. Medium |
| PHP 8 warnings | Hundreds of "deprecated" notices in the report controllers | Do not break pages but flood the log; clean up progressively. Low |
| Obsolete PHP constructs | None found (no each(), split(), create_function, old string offsets) | Nothing to do |
| Database | PostgreSQL functions, views, raw SQL (about 290 statements) | Not affected |
| Front-end | Screens are server-rendered (Blade + jQuery); the build tooling is old but the built files are already in place | Leave as is; do not rebuild |

# 5. Effort estimate (Option C)

| Step | Effort | Notes |
| --- | --- | --- |
| 1. Move JasperReports templates into the project | 1 day | Do this immediately, regardless of the upgrade (section 6) |
| 2. Set up an upgrade test server (PHP 8.2, Java, ImageMagick, PostgreSQL copy) | 2 days | Infrastructure |
| 3. Dependency upgrade and package replacements | 1 week | Breadcrumbs, proxy, permissions migrations, modules restructure |
| 4. Framework code changes | 1 week | Helpers, dates, routes, paging, mail |
| 5. Rewrite the Dynamics AX SOAP layer and test against AX UAT | 1–2 weeks | Depends on AX test environment availability |
| 6. PHP 8 type and warning clean-up in finance and report code | 1–2 weeks | Iterative, driven by testing |
| 7. Regression testing with business users | 2–3 weeks | ~800 screens, ~145 reports, all finance flows, AX posting |
| 8. Go-live and hyper-care | 1 week | Weekend cut-over, rollback plan |
| Total | 7–10 weeks | One developer full-time + business testers part-time |

# 6. Risks

| # | Risk | Likelihood | Impact | Mitigation |
| --- | --- | --- | --- | --- |
| 1 | Report templates lost – 152 JasperReports templates live in the vendor folder, which is excluded from version control and wiped by a routine dependency install. This risk exists today, not only at upgrade time | High over time | ~120 reports stop working | Move templates into the project folder now (1 day); commit them |
| 2 | Dynamics AX posting breaks after replacing the abandoned SOAP package | Medium | Receipts/invoices not reaching finance | AX UAT environment; test every posting type; keep old server on standby |
| 3 | Hidden PHP 8 errors in amount calculations (empty fields) surface only in production | Medium | Wrong totals or error pages in receipts/terminations | Structured regression of all finance flows; enable error logging review during hyper-care |
| 4 | PDF layouts change with the new PDF engine | High | Cosmetic to moderate | Side-by-side comparison of every PDF; fix CSS |
| 5 | Limited automated tests mean regressions are found late | High | Schedule slippage | Business test scripts per module; add unit tests around finance calculations as part of the work |
| 6 | Permission migration misconfigures menus/roles | Low | Users lose access | Backup roles/permissions; verify each role after migration |
| 7 | Doing the upgrade in parallel with the mobile app | – | Doubles the regression scope and blocks both projects on the same developer | Sequence the projects (section 7) |
| 8 | Not upgrading | – | Unpatched security issues; increasing cost of every future change | Keep the system on the internal network only; schedule the upgrade |

# 7. Recommendation and sequencing

- Immediately (1 day): move the JasperReports templates out of vendor into the project and commit them. This removes the single biggest operational risk found in this review.

- Immediately (half a day + smoke test): move production PHP from 7.3 to 7.4. Laravel 5.7 supports it and all recent development is already verified on 7.4.

- Proceed with the mobile app Phase 1 on the current platform. The mobile API is designed as a self-contained module with portable authentication, so it will carry over to the upgraded platform without rework.

- Schedule the full upgrade (Option C) as a separate project of roughly 2–3 months after mobile Phase 1 goes live, with a dedicated test server, an AX UAT environment, and business testers allocated for the regression period.

# 8. Decisions needed

| Decision | Owner |
| --- | --- |
| Approve moving the report templates and the PHP 7.4 step now | IT manager |
| Approve the full upgrade as a scheduled project and its start date | Management |
| Availability of a Dynamics AX test environment for the upgrade period | Finance / ERP owner |
| Business testers per module for the regression period (2–3 weeks) | Department heads |
| Provisioning of a test server with PHP 8.2, Java and ImageMagick | IT infrastructure |